## README
Son Tra Innovation Fest (SIF) — Website Project
Key Facts
Field | Value
Event | Son Tra Innovation Fest (SIF)
Target timeline | MVP in ~3 days after scope is finalized
Languages | English + Vietnamese (2 languages)
Login/Accounts | Not required (public, free event)
SEO | Not required
CMS (content management system) | Strapi (open-source headless CMS) — client team manages content after handover
How the tabs are grouped
SPECS
Defines WHAT is being built.
• Sitemap & Pages — the confirmed pages, their purpose and priority.
• Content Structure — sections/fields per page and who supplies each piece of content.
• Design — reference-site style choice, brand assets (logo/colors/fonts) status.
• Languages (i18n) — scope of EN/VN content, default language, translation owner.
• CMS (Strapi) — content types/collections, fields, and who manages what in the CMS.
EXECUTION
Task trackers: WHO does WHAT, WHEN, and its current status — one tab per phase.
• Phase 1 — Discovery & Scope | Scoping/setup tasks (decisions, sign-off).
• Phase 2 — MVP Build | MVP build (~3 days): frontend, Strapi, forms, staging handover.
• Phase 3 — Content & Polish | Client content entry, feedback fixes, QA, SEO basics, go-live.
PROJECT TRACKING
• Timeline & Budget — high-level summary of all 3 phases + budget note.
• Decision Log — open questions, the decision made, who decided, and when (replaces a plain Q&A list so answers don't get lost).

## Scope & Requirements
SPECS — defines WHAT is built
Scope & Requirements
This is the boundary of the project.
# | Item | Description | Acceptance Criteria | Client Feedback / Changes
1 | Event information | Static/CMS-driven pages describing the event: Home, Agenda, Location, About, .. | All info pages are live, content editable via Strapi, and correct in both EN and VN with no placeholder text at go-live.
2 | Exhibitor listing | Exhibition and Sponsors pages showing exhibitor/sponsor entries | Exhibitor/sponsor list renders from CMS data (logo, name, booth #, category); adding/removing an entry in Strapi updates the site with no code change.
3 | News | News list page + article detail page | Client can create, edit, publish and unpublish a news article from Strapi; the x latest published articles appear on the homepage automatically.
4 | CMS | Strapi admin for all content types listed in the CMS (Strapi) tab | Client's Editor account can log in, edit every content type in scope, and see the change reflected on the live/staging site after publish.
5 | Two languages | English + Vietnamese across all visitor-facing pages | Every visitor-facing page has both EN and VN versions; a language switcher is present on every page and the choice persists while navigating.
6 | Responsive | Layout adapts to mobile, tablet, and desktop | No broken/overlapping layout at common breakpoints (~360px, 768px, 1024px, 1440px); verified on latest Chrome and mobile Safari.
7 | Basic SEO | Page titles, meta descriptions, and social preview (OG) tags — not full SEO strategy/ranking work | Every page has a unique <title> and meta description; sharing a page link shows a correct title/description/image preview.
# | Item | Reason / Note | Acceptance Criteria
1 | Login / Registration | Public, free event — visitors don't need an account to view any page. | N/A — not built. Any request to add this is a scope change (see Change Log).
3 | Ticketing system | Entry is free; no ticket issuing/validation/QR check-in flow. | N/A — not built.
5 | Advanced analytics | No custom dashboards/funnels/reporting beyond what the hosting/CMS provides by default. | N/A — not built.
6 | Drag & drop page builder | Content is managed via structured Strapi fields, not a visual/free-form page builder. | N/A — not built.

## Sitemap & Pages
SPECS — defines WHAT is built
Sitemap — 9 Pages
# | Page (EN) | Trang (VN) | Purpose / Goal | Priority | Menu Location
1 | Home | Trang chủ | Hero + overview, drive traffic to Attend/Agenda/Exhibitor pages |  | Logo
2 | Attend (Why Attend?) | Tham dự (Vì sao nên tham dự?) | Convince visitors to come: highlights, audience, free-entry info |  | Primary nav
3 | Agenda | Chương trình | Event schedule by day/track/time |  | Primary nav
4 | Exhibition (Layout) | Khu trưng bày (Sơ đồ) | Floor plan / exhibitor layout, list of exhibitors |  | Primary nav
5 | Sponsors (+ Become a Sponsor/Exhibitor) | Nhà tài trợ (+ Trở thành NTT/Nhà triển lãm) | Sponsor tiers/logos + inbound application form |  | Primary nav
6 | Location | Địa điểm | Venue address, map, directions, transport/parking info |  | Primary nav
7 | News | Tin tức | Updates/announcements list (managed via CMS) |  | Primary nav
8 | About Us | Về chúng tôi | Event background, organizer, mission |  | Primary nav
9 | Contact Us | Liên hệ | Contact form + info (email/phone/social) |  | Primary nav
Final confirmed page count: | 9

## Content Structure
SPECS — defines WHAT is built
Content Structure — Sections per Page
Page | Section / Block | Field(s) needed | Content Owner | CMS-managed? | Status
Home | Hero banner | Title, subtitle, date, venue, CTA button, background image/video | Client | Yes
Home | Event highlights / stats | 3-4 stat tiles (attendees, exhibitors, speakers, days) | Client | Yes
Home | About teaser | Short intro text + link to About page | Client | Yes
Home | Sponsors strip | Sponsor logos (pulled from Sponsors collection) | Client | Yes
Home | Latest news preview | 3 latest News items (auto-pulled) | Client | Yes
Attend | Why Attend hero | Headline + supporting copy | Client | Yes
Attend | Audience / benefits | Who should attend, list of benefits | Client | Yes
Attend | Free entry / registration info | Ticket info (free), any RSVP link if needed | Client | Yes
Agenda | Schedule table | Day, time, session title, speaker, track, location | Client | Yes
Agenda | Download agenda (optional) | PDF agenda file | Client | Yes (media)
Exhibition | Floor plan / layout image | Floor plan graphic (image or interactive map) | Client | Yes (media)
Exhibition | Exhibitor list | Company name, logo, booth #, category, description | Client | Yes
Sponsors | Sponsor tiers | Tier name, benefits, logos per tier | Client | Yes
Sponsors | Become a Sponsor/Exhibitor form | Company, contact, email, phone, package interest, message | Dev (form) / Client (review) | Form submissions only Send to an Email
Location | Venue details | Address, map embed, directions, parking/transport notes | Client | Yes
News | News list + detail | Title, cover image, date, body content, category | Client | Yes
About Us | Organizer story | Mission, background, organizer logo/info | Client | Yes
Contact Us | Contact form + info | Name, email, message; plus phone/email/social links | Dev (form) / Client (info) | Form submissions only Send to an Email
Global | Header / Nav | Logo, menu items, language switcher | Client (logo) / Dev (build) | Menu via CMS (optional)
Global | Footer | Quick links, social icons, contact, copyright | Client | Yes

## Design
SPECS — defines WHAT is built
Design Direction
Reference sites shared by client (pick closest match)
Reference site | Style notes | Best-fit for SIF section | Selected? (Y/N) | Comments
Hannover Messe | Industrial, bold, tech-forward, dense info | Exhibition/Agenda density
IFA Berlin | Vibrant hero video, stats-driven, highlight reels | Home hero, highlights
MWC Barcelona | Premium, minimal, strong CTA structure (Attend/Exhibit/Speak) | Overall page structure & CTAs
AI Expo Europe | Content-heavy nav, speaker-focused, pass tiers | Speakers & Sponsors pages
Computex Taipei | News-driven, corporate | News page
Brand & Visual Assets
Logo (SIF) | Available | Brand Guidelines Link
Brand colors | Available / Not yet — need hex codes
Typography | To be chosen by dev if none provided | Web-safe / Google Fonts | <<< MUST BE 100% Compatible with Vietnamese
Photography / venue photos | Available / Not yet — placeholders until provided | Not much for now. 1st Edition Event No photos/Video | We will make designs and Promo Video
Style tone | Modern + tech-forward, with local (Son Tra/Da Nang) identity | Modern / Tech

## Languages (i18n)
SPECS — defines WHAT is built
Languages / Localization Scope
Item | Decision | Notes
Languages | English + Vietnamese | Confirmed
Default language | English | TBD — likely Vietnamese (local event) with EN toggle
Translation source | DN365 Manually Translates ALL Content, including Website Buttons/Titles | Client team writes VN content; EN translation by client or dev (confirm who)
Fields needing translation | All visitor-facing text | Titles, body copy, form labels, buttons, nav menu, agenda session titles
Non-translatable content | Images, dates, addresses (unless needed), form field data

## CMS (Strapi)
SPECS — defines WHAT is built
CMS Setup — Strapi Content Types
Content Type | Type | Key Fields | Managed by Client? | Notes
Site Settings | Single Type | Logo, contact info, social links, footer text | Yes | Global settings, one entry
Home Page | Single Type | Hero fields, highlights, stats | Yes
Agenda / Sessions | Collection Type | Day, time, title, speaker (relation), track, location | Yes | Sortable by date/time
Exhibitors | Collection Type | Company name, logo, booth #, category, description | Yes
Sponsors | Collection Type | Name, logo, tier, link | Yes
Sponsor/Exhibitor Applications | Collection Type (form entries) | Company, contact, email, phone, package, message, status | Yes (view/manage only) | Populated by public form submissions
News / Articles | Collection Type | Title, cover image, date, body, category | Yes
Contact Submissions | Collection Type (form entries) | Name, email, message, date, status | Yes (view/manage only)
Location / Venue | Single Type | Address, map coordinates, directions text, images | Yes
About Us | Single Type | Story, mission, organizer info | Yes
Access & Roles
Editor (client team) | Create/edit/publish content only, no schema changes

## Phase 1 - Discovery & Scope
EXECUTION — WHO does WHAT, WHEN (this phase only)
Phase 1 — Scope & Setup Tasks
Goal: lock the SPECS tabs (Sitemap, Content Structure, Design, Languages, CMS) and resolve the Decision Log so Phase 2 can start with no open unknowns.
Step | Task | Description | Owner | Deliverable | Related tab | Status
1 | Kickoff & requirements capture | Capture pages, content, timeline, languages, CMS choice | Client + Dev | Requirements captured (this workbook) | README | In progress
2 | Confirm sitemap | Client confirms final the number of pages and priority | Client | Sitemap & Pages tab locked | Sitemap & Pages | In progress
3 | Confirm content structure | Client confirms sections/fields per page and who supplies each | Client | Content Structure tab locked | Content Structure | In progress
4 | Choose design direction | Client picks closest reference style; provides logo/colors/fonts if available | Client | Design tab locked + brand assets received (or dev proceeds with placeholder palette) | Design | Open
5 | Confirm language scope | Confirm default language, URL structure, who translates EN/VN | Client | Languages tab locked | Languages (i18n) | Open
6 | Confirm CMS schema | Dev proposes Strapi content types, client confirms fields/ownership | Dev (draft) / Client (approve) | CMS tab locked | CMS (Strapi) | Open
7 | Resolve open questions | Answer all items in the Decision Log (venue, dates, hosting access, notifications, etc.) | Client | Decision Log fully answered | Decision Log | Open
8 | Phase 1 sign-off | Client confirms all SPECS tabs + Decision Log are final | Client | Written go-ahead to start Phase 2 build | All SPECS tabs | Open

## Phase 2 - MVP Build
EXECUTION — WHO does WHAT, WHEN
Phase 2 — First Version / MVP (Target: ~3 days)
Day | Task | Description | Owner | Deliverable | Depends on | Status

## Phase 3 - Content & Polish
EXECUTION — WHO does WHAT, WHEN
Phase 3 — Content & Final Polish
Step | Task | Description | Owner | Deliverable | Depends on | Status

## Timeline & Budget
PROJECT TRACKING — cross-cutting, spans all phases
Timeline & Budget Overview
High-level summary only — see the Phase 1/2/3 Tasks tabs (green, EXECUTION group) for the detailed day-by-day breakdown.
Phase | Scope | Key Deliverables | Owner | Est. Duration
Phase 1 — Scope & Setup | Finalize pages, content structure, design direction, CMS schema | SPECS tabs signed off; Decision Log resolved | Client + Dev
Phase 2 — First Version / MVP | Build frontend (9 pages) + Strapi CMS + connect forms | Working MVP site with placeholder/sample content, deployed to staging | Dev | ~3 days
Phase 3 — Content & Polish | Client enters real content via Strapi; dev fixes feedback, responsive QA, basic SEO/meta tags, final testing, deploy live | Live production website | Client (content) + Dev (fixes/deploy) | TBD based on content readiness
Budget Note
Budget: ** VND (dev effort only). Domain + hosting already covered by client. Client team owns all content entry and translation.

## Decision Log
PROJECT TRACKING — cross-cutting, spans all phases
Decision Log — open questions, tracked to a decision
Unlike a plain question list, every row here is expected to end with a recorded decision
# | Question | Asked to | Decision / Answer | Decided by | Date decided | Status | Cột 1
1 | Event date & venue (exact address) | Client | October 2nd and 3rd |  |  | Open
2 | Final confirmed page list | Client | Attached Image on the Right |  |  | Open
3 | Logo / brand colors / fonts — do these exist or does dev design them? | Client | Link |  |  | Open
4 | Default language (VN or EN) | Client | English |  |  | Open
6 | Hosting environment details (server specs, OS, existing setup) for Strapi + frontend deploy? | Client |  |  |  | Open
7 | Domain DNS access — who configures it for going live? | Client |  |  |  | Open
8 | Do forms (Speaker/Sponsor/Contact) need email notifications on submission? | Client |  |  |  | Open
9 | Any existing content (past event photos/text) to reuse, since this may be first edition? | Client |  |  |  | Open
10 | Analytics needed (even without SEO) — e.g., basic visitor count? | Client |  |  |  | Open
11 | Deadline / go-live date? | Client |  |  |  | Open

## Change Log
PROJECT TRACKING — cross-cutting, spans all phases
Change Log — changes to scope, budget, or timeline
Anything not listed in the Scope & Requirements tab (SPECS group) is out of scope by default. A client or dev request to add/remove/change something after Phase 1 sign-off gets logged here, with its impact and approval
# | Date | Requested by | Change description | Impact (Scope/Budget/Timeline) | Approved by | Status
1 |  | e.g. Client | e.g. Add a Google Maps embed on the Location page (not in original scope) | e.g. +0.5 day, no budget change |  | Example — edit or delete
2
3
4